## BarChart
|  | Interval = | 4 | Calendar Days |  | Enter Spec No. J1 |  |  | XX06-99 | [7 empty] | Maintenance Building #3
|  | In Working Days |  | Odd # Years Black Even # Years Red |  | & Project Name in R1 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Tasks | Cost $s | Task starts Days after 10/18/05 | Days for Task | Task Start date | Task End date | Total Days & (Non-WDs) | 2005-10-10 | 2005-10-14 | 2005-10-18 | 2005-10-22 | 2005-10-26 | 2005-10-30 | 2005-11-03 | 2005-11-07 | 2005-11-11 | 2005-11-15 | 2005-11-19 | 2005-11-23 | 2005-11-27 | 2005-12-01 | 2005-12-05 | 2005-12-09 | 2005-12-13 | 2005-12-17 | 2005-12-21 | 2005-12-25 | 2005-12-29 | 2006-01-02 | 2006-01-06 | 2006-01-10 | 2006-01-14 | 2006-01-18 | 2006-01-22 | 2006-01-26 | 2006-01-30 | 2006-02-03 | 2006-02-07 | 2006-02-11 | 2006-02-15 | 2006-02-19 | 2006-02-23 | 2006-02-27
Project Dates |  |  | Enter FWD= | 2005-10-18 | #VALUE! | #VALUE! | 2005-10-10: 1; 2005-10-14: #VALUE!
Mobilize | 1000 | 1 | 2 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-10-22: Mobilize
Clear Site | 5500 | 2 | 2 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-10-22: Clear Site
Set Stakes | 1600 | 4 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-10-26: Set Stakes
Dig Foundations | 12000 | 5 | 4 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-10-30: Dig Foundations
Clean up | 1000 | 9 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-11-03: Clean up
Set Forms | 4800 | 10 | 3 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-11-07: Set Forms
Place Rebars | 12000 | 13 | 2 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-11-11: Place Rebars
Place Footings | 23000 | 15 | 10 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-11-23: Place Footings
Place Slab | 34000 | 21 | 3 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-11-23: Place Slab
Strip Forns | 3400 | 27 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-12-01: Strip Forns
Clean up | 1000 | 28 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-12-01: Clean up
Deliver Dry Wall | 12000 | 34 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2005-12-09: Deliver Dry Wall
Frame Bldg | 30000 | 31 | 25 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-01-14: Frame Bldg
Install Drywall | 15000 | 36 | 27 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-01-26: Install Drywall
Tape Drywall | 6500 | 60 | 10 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-02-03: Tape Drywall
Roof | 3400 | 41 | 32 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-02-11: Roof
Gutters | 4000 | 75 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-02-11: Gutters
Doors & Windows | 9000 | 35 | 17 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-01-10: Doors & Windows
Painting | 9700 | 51 | 29 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-02-19: Painting
Clean up | 2000 | 82 | 2 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!; 2006-02-27: Clean up
Demobilize | 2000 | 84 | 1 | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE! | Demobilize
| 192900 | [5 empty] | 2005-10-18: Submitted: ABC Construction Inc.
by ______________________ Date______________
Title_______________________________________
| Enter Contractor's Name ==> | ABC Construction Inc.
Math Below - Don't disturb. | bar: 2005-10-10 to 2005-10-14
|  |  |  | #VALUE! | #VALUE! | #VALUE! | 2005-10-10: #VALUE!; 2005-10-14: #VALUE!
Math abopve - Don't disturb. | bar: 2005-10-10 to 2005-10-14
Submitted: ABC Construction Inc.
by ______________________ Date______________
Title_______________________________________
Start of Contract Time
End of Contract Time

## Help
Same as ufHelp1 displayed with Help icon. This can be used to print Help
| Ranges | Ranges used to load ufHelp1.
C A U T I O N S |  | If ranges are expanded messages in Col a
| Help1 Beg | will be added to user form automatically
Always use the "Rows" menu buttons to add or delete rows. |  | as will any changes in the text.
If expand beyond 15 lines, a vertical
Don't: 1. add or delete any Columns. |  | scroll bar will be added automatically.
2. make any entries on sheets other than "BarChart".
3. delete or alter "BarChart" sheet Rows 1 to 4.
4. alter cells in "BarChart" sheet except in Columns A to D.
5. Disturb "Math" which is in Columns A:G, 20 rows below "Total".
If the Toolbar is lost, to restore it, either:
Select BarChart!J1, press [F2] key, press [Enter] key, or
"Tools"-"Macros"-"AddTB2"-"Run"
Open "Help" sheet to print all of Help Screens.
Double Click in Yellow field to close any Help window | Help1 End
Setup Chart
Help2 Beg
1. Type in project Spec. No. title in cell J1 (Range name "SpecNo") and
Project Title in cell R1 (Range name "Title").
Both will go across other cells & be printed on both charts.
SpecNo sets the default file name for saving the file.
2. Enter First Working Day for project in cell E4 (Range name "Date1").
3. Enter plotting interval in calendar days in cell D2 (Range name "Interval").
This will also cause bars to update.
4. Determine the number of tasks to be included. This can be changed later.
5. Use "Rows"-"Delete Selected Rows" to remove the excess.
6. Use "Rows"-"Add New Tasks" to add tasks.
7. If a task is not continuous, use a row for each continuous segment.
8. Enter Contractor's name in range "Contractor" (Col C below Total)
NOTE: It is not necessary to remove existing task rows.
They can be used by changing the entries in Cols. A to D.
Help2 End
Data Entry
Help3 Beg
1. Data in Columns A to D, Rows 5 and below may be entered or changed.
2. Use "Rows" - "Add New Tasks" button to add more lines. It puts in formulas.
Rows are added at bottom. See 5 below to move.
3. Use "Rows" - "Delete Selected Rows" to delete rows.
4. Blank rows may be inserted to force bars to next page for printing with
"Rows" - "Insert Blank Row" button.
5. The "Move Row Up" & "Move Row Down" buttons can be used to change the
position of a task in the list. They work only when an entire row is selected
first. The row moved will stay selected so the button can be clicked repeatedly
to move the selected row multiple times. De-select the row when finished.
6. Task length and times to start are in Working days.
7. Cols. E, F & G show elapsed Calendar days.
Help3 End
Updating Bars
Help4 Beg
1. The bar chart is not drawn nor updated directly by making the task entries.
Use the "Update Bars" button at any time to draw or update the bars.
2. The task descriptions are included following the bars when the bars are drawn.
The "Hide/Show" menu "Hide/Show Tasks on Bars" button toggle the tasks
following the bars between visible and hidden.
3. Updating also adds signature block & moves "End of Contract Time".
4. Updating occurs automatically whenever plotting interval is changed.
Help4 End
View or Print
Help5 Beg
1. Use "Hide/Show" menu buttons to show the desired element for printing.
2. Use "Print" menu "Select Printer" button to change printers.
3. Use "Print" menu buttons to preview either chart.
Click on "Print" in the preview bar to print the previewed chart.
4. If Cost-Time chart does not display, on BarChart sheet, click on Update.
Help5 End

## Cost Data
Date | Cum Earned | X | Y | BarTasks | TRUE
#VALUE! | 0 | 0% | 0 | Warn
#VALUE! | #VALUE! | 4% | #VALUE! | Days | #VALUE!
#VALUE! | #VALUE! | 8% | #VALUE! | FWDRow | 4
#VALUE! | #VALUE! | 12% | #VALUE! | LastRow | 25
#VALUE! | #VALUE! | 16% | #VALUE! | Ntasks | 21
#VALUE! | #VALUE! | 20% | #VALUE! | LastCol | 43
#VALUE! | #VALUE! | 24% | #VALUE! | CkWD | #VALUE!
#VALUE! | #VALUE! | 28% | #VALUE!
#VALUE! | #VALUE! | 32% | #VALUE!
#VALUE! | #VALUE! | 36% | #VALUE!
#VALUE! | #VALUE! | 40% | #VALUE!
#VALUE! | #VALUE! | 44% | #VALUE!
#VALUE! | #VALUE! | 48% | #VALUE!
#VALUE! | #VALUE! | 52% | #VALUE!
#VALUE! | #VALUE! | 56% | #VALUE!
#VALUE! | #VALUE! | 60% | #VALUE!
#VALUE! | #VALUE! | 64% | #VALUE!
#VALUE! | #VALUE! | 68% | #VALUE!
#VALUE! | #VALUE! | 72% | #VALUE!
#VALUE! | #VALUE! | 76% | #VALUE!
#VALUE! | #VALUE! | 80% | #VALUE!
#VALUE! | #VALUE! | 84% | #VALUE!
#VALUE! | #VALUE! | 88% | #VALUE!
#VALUE! | #VALUE! | 92% | #VALUE!
#VALUE! | #VALUE! | 96% | #VALUE!
#VALUE! | #VALUE! | 100% | #VALUE!
Red Line |  | 0% | 0%
|  | 20% | 0%
|  | 102% | 100%